## Sheet1
Key | Deadlines
 | time axis 2025-01-13 to 2025-03-02
Project plan and scope | Responsible person(s)
Submission of non-disclosure agreements | All | TRUE | bar: 2025-01-13 to 2025-01-15
Team charter | All | TRUE | bar: 2025-01-15 to 2025-01-17
Identify project objectives | All | TRUE | bar: 2025-01-17 to 2025-01-19
Define project scope | All | TRUE | bar: 2025-01-17 to 2025-01-19
Assign team roles and responsibilities | All | TRUE | bar: 2025-01-17 to 2025-01-19
Develop project plan | Bev Grantham | TRUE | bar: 2025-01-17 to 2025-01-20
Data preparation
Review Study Group dataset | All | FALSE | bar: 2025-01-20
Clean and pre-process the data | Davide Cascarin | FALSE | bar: 2025-01-21
Consider use of external data | Emmanuel Wagaba | FALSE | bar: 2025-01-22
Exploratory analysis
Generate summary statistics | Bev Grantham | FALSE | bar: 2025-01-23
Identify anomalies and outliers | Jessy Pardi | FALSE | bar: 2025-01-24
Develop visualisations of links between variables | Emmanuel Wagaba | FALSE | bar: 2025-01-25
Analysis and modelling
Analyse discount allocation | Davide Cascarin | FALSE | bar: 2025-01-26 to 2025-01-28
Evaluate discount effectiveness | Jessy Pardi | FALSE | bar: 2025-01-29 to 2025-01-31
Perform demographic and trend analysis | Bev Grantham | FALSE | bar: 2025-02-01 to 2025-02-03
Identify gaps and missed opportunities | Davide Cascarin | FALSE | bar: 2025-02-04 to 2025-02-06
Quality Assurance | Emmanuel Wagaba | FALSE | bar: 2025-01-26 to 2025-02-06
Insights, Recommendations, and Reporting
Develop actionable recommendations to optimize discount allocation. | All | FALSE | bar: 2025-02-06 to 2025-02-09
Prepare a final presentation for stakeholders | Jessy Pardi | FALSE | bar: 2025-02-07 to 2025-02-10
Pitch rehearsal | All | FALSE | bar: 2025-02-10 to 2025-02-11
Initial pitch | All | FALSE | bar: 2025-02-12
Interim review | All | FALSE | bar: 2025-02-12 to 2025-02-17
Final pitch rehearsal | All | FALSE | bar: 2025-02-16 to 2025-02-17
Final pitch | All | FALSE | bar: 2025-02-18
Final document submission | Bev Grantham | FALSE | bar: 2025-02-19 to 2025-02-24
Individual reflections | All | FALSE | bar: 2025-02-24 to 2025-02-27
Percentage completion
20%